## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | Team Leader | 2025-12-25 | Redefine the project scope if necessary, and assign the tasks to other team members. | No such occurance so far. | Open
| add new team members | One or more team members join the team | 1 | 1 | 3 | 3 | Team Leader | 2025-12-25 | Onboard them and delegate tasks to them according to theri skillset. | No such occurance so far. | Open
| Lack of motivation or responsibility | One or more team members do not complete tasks as agreed | 3 | 4 | 3 | 36 | Team Leader | 2025-12-25 | Adjust project scope to commodate their needs, shrink project scope if necessary. | No such occurance so far. | Open
Communication | duplicate work | On or more team members do the same work | 2 | 2 | 3 | 12 | Team leader | 2025-12-25 | Some work duplication is actually necessary as insurance against unpredictable demotivation of some teammates as long as the team members in question are aware and willing, for example for the extra learning. | UI and backend leader is jointing working to frontend. Progress is reviewed weekly. | Open
| worked on wrong components | Team members work on components relevant to the project but not needed at the current iteration. | 3 | 3 | 3 | 27 | The whole team | 2025-12-25 | At the start of each iteration, the team leader confirms the component breakdown with the group; each member’s assigned component is logged in meeting minutes. Mid-week, a short async check (Discord/Slack/Drive) verifies progress alignment. If a mismatch is discovered, reassign tasks immediately and document the change. | No such occurance so far. | Open
| useless work | Codes not needed for the project is developed. | 3 | 2 | 3 | 18 | The whole team | 2025-12-25 | Before implementation, every feature must be tied to an existing user story or acceptance criterion. Any extra ideas are logged in a backlog for future consideration but not coded during the current iteration. During weekly check-ins, the team leader and QA lead verify that ongoing work maps directly to agreed deliverables. | No such occurance so far. | Open
| inconsistent work | Performance of team members vary. | 3 | 3 | 3 | 27 | The whole team | 2025-12-25 | Define minimum quality standards for each deliverable (documentation, code review, testing). During weekly check-ins, the team leader and QA lead review progress against these standards. If a teammate struggles, pair programming or mentoring is arranged before reassigning tasks. Any handover of work must be documented in meeting minutes to ensure continuity. | Not implemented. | Ongoing
Requirements | unclear requirements | Task requirement is not clear. | 3 | 3 | 3 | 27 | Configuration Leader | 2025-12-25 | For each feature, draft user story and acceptance criteria before coding; QA lead validates clarity during weekly review. | User story partially drafted. | Ongoing
| scope creep | Project scope expands before completing exiting reqruiements. | 1 | 3 | 3 | 9 | The whole team | 2025-12-25 | Any proposed scope change must be logged in backlog; only reviewed during iteration planning; no mid-iteration changes unless unanimous. | No such occurance so far. | Open
| constant requirements changes | Project requirement changes constantly. | 2 | 3 | 3 | 18 | The whole team | 2025-12-25 | Same as scope creep: changes logged and deferred until iteration planning; no mid-iteration requirement shifts unless unanimously agreed. | Not applicable at Iteration 0 | Open
Management | improper task assignments | Task is assigned to team member without the needed skillset. | 3 | 3 | 3 | 27 | Team leader | 2025-12-25 | Before assigning, confirm skills in meeting; if mismatch occurs, reassign within 48 hours and log in meeting minutes. | No such occurance so far. | Open
| improper planning | Project planning in unrealistic. | 3 | 4 | 3 | 36 | Team leader | 2025-12-25 | At the start of each iteration, freeze user stories into Jira/Google Sheet; team leader checks deliverable completion against sheet in weekly meeting. | Jira project created are the team is learning to use it. | Open
| lack of management skills | Team leader is not able to meaninfully coordinate the team. | 4 | 3 | 3 | 36 | Team leader | 2025-12-25 | Team leader holds a 15-minute weekly coordination check to align on priorities; teammates provide feedback on workload clarity; if coordination gaps persist, escalate to faculty for guidance. Leadership responsibilities may be rotated for one iteration to build resilience. | Coordination and alignment is discussed and arranged in weekly meeting. | Ongoing
Technology competence | Not familiar with the framework used | Team members are unfamiliar with the framework used. | 4 | 4 | 3 | 48 | The whole team | 2025-12-25 | Each member follows one official tutorial; pair program one session to ensure baseline competence; consult AI for debugging. | Not implemented. | Ongoing
| Not familiar with the programming language used | Team members are unfamiliar with the language used. | 5 | 5 | 3 | 75 | The whole team | 2025-12-25 | Each member completes a short tutorial or exercise in the required language before coding their assigned module. Pair programming is used during the first implementation tasks to accelerate learning. Code templates and style guides are shared in the repo to reduce errors. AI tools may be used for syntax support, but teammates must review logic for correctness. | Not implemented. | Ongoing
| Not familiar with unit testing | Team members are not familiar with unit testing. | 5 | 5 | 3 | 75 | CI/CD leader | 2025-12-25 | Set up pytest by iteration 2; require one test per function; AI suggests edge cases but CI/CD lead validates before merge. | Not implemented. | Open
| Other technology incompetence | Other technically insufficiencies unrelated to the aforementioned categories. | 5 | 3 | 3 | 45 | The whole team | 2025-12-25 | If an unknown technical gap arises, schedule a 2-hour research sprint, document findings in the meeting minutes, and escalate to instructor or external resources if unresolved. | Not implemented. | Open
| Not familiar with Git | Team members are not familiar with git and HitHub. | 3 | 2 | 3 | 18 | The whole team | 2025-12-25 | Learn to use Git and GitHub. | One teammate was not familiar with git and learn it online. | Open
Design and implementation | Improper design | Software design is unrealistic. | 3 | 4 | 3 | 36 | The whole team | 2025-12-25 | Before implementation, create simple UML diagrams or system sketches to validate architecture. Review designs as a group during weekly meetings; QA lead checks consistency with requirements. Use AI for alternative design suggestions, but final approval must come from peer review. Revisit design decisions at iteration boundaries to confirm feasibility with time and skills. | Sketch shared in Iteration 0 presentation. | Open
| improper technology stack | Tech stack chosen is not suitable for the project. | 3 | 3 | 3 | 27 | The whole team | 2025-12-25 | At project start, compare proposed stack against course requirements, team skill levels, and available support (tutorials, documentation). The team leader records rationale for chosen stack in SPPP. If major blockers arise, evaluate alternative stack options in iteration review, with decision logged and approved by majority vote. AI tools may be used for pros/cons analysis but not as the sole deciding factor. | We use Chat-GPT to evaluate if the project tech stack is sensible and adjust it according to our skillset. | Open
| Messy code | Code is unwieldy and unmanageble | 4 | 3 | 3 | 36 | The whole team | 2025-12-25 | Enforce code linting (flake8/eslint); require review by at least one peer; use AI suggestions but accept changes only after peer approval. | Not implemented. | Open
Testing | Not enough testing | Not enough testing or testing does not fully capture all errors. | 3 | 3 | 3 | 27 | CI/CD leader | 2025-12-25 | Enforce coding standards through automated linters (flake8 for Python, ESLint for JavaScript). Every pull request must undergo peer review by at least one teammate. AI tools can suggest cleanups, but changes are only accepted after peer approval. Regular refactoring sessions are scheduled at the end of each iteration to keep the codebase maintainable. | Not yet implemented | Open
Integration and deployment | Not enough time for integration and deployment | There is not enough time for integration and deployment. | 4 | 4 | 3 | 48 | CI/CD leader | 2025-12-25 | Reserve last week of each iteration for integration; enforce ‘demo-ready’ rule—each iteration must produce a working deployable build. | Not yet implemented | Open