## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/11 - 09/25 | Set up repo Push backend skeleton Implement using OCR to read PDFs with one layout. Implement dashboard prototype using sample data. Adopt flat hierarchy to enable teammates to contribute as they see fit and account for future.demotivation. PDFs in one layout can be locally read and analyzed to give commerically insightful metric such as monthly performance and cost anomalies. Static data is upload to Azure with endpoints publicly accessible. Write Risk Management plan to be implemented in the next iteration. | Machine learning is harder to set up and train then expected. Tried to use AI for analysis but result is not stable; should use deterministic algorithm given accounting information has low error tolerance. Interface between different parts of the project are not yet finalized. Machine learning is time-expensive to train with unpredicatble returns. Frontend is still using local, static data for visualization, creating a integration tech debt to be paid. Such tech debt is necessary given that UI lead needs some concrete data to start prototyping. A lot of time is spent on tech stack shopping. For example, some time is spent on experimenting whether the backend should be deployed in PostgreSQL or SQLite considering each's difficulties and security concerns. | Coordination tools are scattered Team members start developing without following Jira Reporting burden is underestimated Spent a lot of time comparing different tools, e.g., Notion, Jira, or Google Docs. The team has to implement AGILE principles without full understanding. There is some idling time where one temmate's work depends on another's work, e.g, visualization depends on generation of analysis which didn't exist until the end of this cycle. Project scope, team skillset, personalites, dataflow influence each other and is hard to plan beforehand. | Chose the sufficient good and stick to it instead of shopping for the perfect product: Google Docs solely for reporting, Jira for progress tracking Treat development is both product building and cartographing the relationship people, product, and project, and to identify bottlenecks and unexpected opportunity for synergy among teammates. Relax role boundary, let teammates decide where they would like to contribute to better utilize their initiatives. Prioritize working code over comprehensive documentation in accordance with Agile principle. Draw out dataflow diagram and pinpoint points of integration one by one. Prioritize building reliable, simple functions over planning new features. Address integration problems before tech debt interest incurs. Draft SPPP and Risk Managment. | 0 | 1 | 3 | 0 | 0 | 120.25 | 20 | 0.75 | 28 | 15.5 | 17.5 | 26.5 | 7 | 16 | 9 | LOC: 2,580 No. of Classes: 6 No. of Methods: • Python Methods: 32 methods • Frontend Functions: 14 functions/components Dependencies: • Backend Dependencies: 13 packages • Frontend Dependencies: 15 packages (from package.json) Project Structure: • Python Files: 9 files • Frontend Source Files: 2 main files (App.tsx, index.tsx) • Configuration Files: Multiple (.env, Dockerfile, web.config, etc.)

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Contribution_Boya
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11-9/17 | 6 | 6 | 1 | 0-learning JIRA 1-define the security requirement 2-design a core code in risk management 5-communicate what functions should be in the program | 3 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | Use chatgpt to learn JIRA and risk management | 1.Wirte 20 line code about risk management tape， began to design and introduce the risk control module as an extension of the original analysis function. 2.communicate with teams and confirm require about program | 1.not compelet about the code 2.something about security require is still unclear | 1.keep learning about risk management 2.giving more time to test the program we already design
2 | 9/18-9/25 | 7 | 7 | 1 | 0-learning risk management 2-design risk management program 3-integrate the program with last week design | 3 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | use chatgpt to learn JIRA and risk management | 1.integrate the program 2. The main.py has also been modified to enable it to call the risk control module after parsing the rent report to conduct risk assessment and prompt for the results | 1.lots of bug in my program 2.The merged program has not been tested yet | 1.Implement more detection rules 2.Supplementary test cases 3.Improve the document

## Contribution_MingLeong
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader, Domain Expert
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/11 - 09/17 | 21 | 18 | 2.5 | 0 - learn Jira, SCRUM, Azure 1 - explore overlap between cutomer needs and team's capabilities 5 - make project plan, recruit members, set up dashboard, portal available hours, gather contact infomration from members; set up communication rules and workflow 6 - set up git, upload sample data 7 - research similar products, prepare presentation | 3 | 3 | 0 | 12 | 0 | 1.5 | 1 | 0.5 | Use chatgpt to learn Jira, understand reporting requirement in relation to grading guide, making progressing tracking easier by following a TODO lists with clear deadlines. Use Cursor to experiment the feasibility of training a machine learning model to read a sample set of PDFs. | 1. Write Management Plan of SPPP. 2. Set up Sprint on Jira. 3. Allocate tasks according to team roles. 4. Create portal on Notion to centralize information sharing. 5. Set up organizational repo. | 1. Not familiar with SCRUM, prioritization of items may not be suitable for teammates' capacity, estimation of work hours is arbitrary. 2. Response time of teammates is unpredictable, leading to frequent idling. 3. Reporting requirements compete with hours that could have spent on coding. 4. Lack of detailed understanding on the technologies teammates use lead to extra time spent on understanding the feasibilities of our project. | 1. Learn SCRUM and learn by doing. Use the iteration to guage team's overall style and capacity, and adjust in the next iteration. 2. Collect class schedules of all members and use AI to auto-generate avaiable hours for communication; reduce team meeting hours to minimum; clearly defining goals of metting beforehand 3. Use chat-gpt to checklist items to reduce cognitive load of document reading. 4. Toy with technologies temmates use to improve the details and qualities of my directions. | 5. Review team's response to current workflow and solve conflicts as arised. 5. Follow up on reporting. 3. Get a table filled with data ready either by ML, OCR, or from external source so teammates can have something concrete to work on. | 20
2 | 09/18 - 09/26 | 25 |  |  | 2 - training machine learning model to test feasibility 5 - learn machine learning from Zihan 5 - deploy backend to Azure. | 2 | 1 | 3 | 10 | 3 | 4 | 2 |  | Use to write part of SPPP. Use it to write coding standard then use it to automatically enforce it through AI-assisted code review. | 1. Review connection between high-level customer demand and proposed analysis process. 3. Train machine learning model; write deterministic analysis based on sample data. 4. Write SPPP. 5. Get the Azure endpoints running. 6. Configure host environment. | 1. SCRUM is not feasible as early phase of project as project requirements and team knowledge about our own capabilities and limits co-evolve with each other, making a waterfall goal-to-implemention approach to project management too rigid to not taken account new contextual knowledge such as clarity gained on customer needs after discussion, or the limitation of our time and resources. 2. Temmates are vastly different in schdules, implementation skills, domain of expertise, language, and attitudes. Aligning these factors towards product delivery requires a unifying motivation. 3. Machine learning model is time-expensive to configurate, train, and iterate. | 1. Adopt a flat hierarchy I learnt from two successful companies: Valve and Netflix. Teammates are free to contribute as they see fit without following the roles their titles entail. This simultaneously solves the scheduling problem and serves as an experiment to measure at which part of the project are each teammate most willing to contribute in. 2. Our unifying motivation is to get good grades and deliver a product worthy to be put into our CVs or even be sellable. I guide this project with these goals in mind. But to actually motivate without sounding like empty corporate bromide, I have to lead by example and show by action that I am to bear heavy workload. 3. Treat machine learning PDF reading solution as high-risk, high-reward development; pay the config cost early to gain more time to experiment training throughout the development cycle while engaging in other tasks that demand human input. | 3. Integrate different components of the project. 5. Address team conflicts, e.g., scheduling, response time. | 20

## Contribution_Sujan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/11 - 09/17 | 10 | 9 | 1 | 0 - Learn Git, GitHub, ML Pipeline, SQLAlchemy, React 1 - Flask API, React Components, DB models, ML Pipeline 2 - Frontend: React(TypeScript), Backend: Flask(Python), DB: SQL Server(AYQ Database) | 6 | 1 | 2 | 0 | 0 | 0 | 0 | 0.5 | Use GPT Plus for React(Typescript), Git and GitHub, SQLAlchemy tutorial for connection between Python and Database, ML Pipeline Stages for implementation | 1. Set up Git and GitHub, analyzed the templates and project requirements. 2. Created a new branch, pushed my folder onto the branch and perform commit. | 1. New to React(Typescript), Github. 2. Not so familiar with practical implementation of ML pipeline. | 1. Pursuing React(Typescript) tutorials. 2. Got through Git and GitHub and the gitbash commands. | 1. Virtual Environment setup 2. Unit Testing 3. ML pipeline practical implementation | 10
2 | 09/18 - 09/26 | 9 | 8 | 1 | 3 - Seperation between frontend, backend and database 4 - Unit testing before integration 5 - communication/management 6 - Virtual Environment needed | 0 | 0 | 0 | 3.5 | 3 | 0.5 | 1 | 0.5 | Use GPT Plus for seperation of code between frontend, backend, and database, integrating all the three components(frontend , backend, database), ML pipeline practical implementation, virtual environment setup | 1. Unit testing of each component. 2. Virtual Environment setup successfully. 3. Executed the code locally in virtual environment. 4. ML pipeline implementation for anamoly detection | 1. ML pipeline implementation. 2. Python module's path to be added to create virtual environment 3. Database connection with the backend. | 1. Fundamental ML pipeline implementation 2. Paths added to environment variables and virtual environment established successfully. 3. Flask specified as to which DB to be used with DB credentials | 1. Implementation of new methods and tables. 2. Testing results with new or more volume of sample data. | 14

## Contribution_Xinyu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA and CI/CD part
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/11 - 09/17 | 8 | 6 | 2 | 0 – read CI/CD tutorials, learn GIthub and JIRA details 1 - learn high level requirements, understand the project 2 – draft initial QA plan, CI/CD testing plan 5 – meeting follow-up, QA updates 6 – configure GitHub Actions pipeline | 2 | 1 | 2 | 0 | 0 | 2 | 1 | 0 | -Used ChatGPT to refine QA test case structure; Deepseekt suggested CI configurations. -Need to adapt manually | 1.Drafted CI/CD plans, using a slide to show what I supposed to do 2.QA Test Strategy v1 3.set up git | 1. not familiar with JIRA, need time to learn 2. Since need other workmate to wirte code basis for testing, hard to write code 3. communication is not clear enough, some questions have not solved | 1.Ask for endpoint skeletons; write mocks, try CI tests on PRs 2.Set standups + decision log, track questions with owner & due date. | 0 – continue JIRA and QA tutorial 1 – refine requirements 3 – implement basic CI test | 8
2 | 09/18 - 09/26 | 10 | 8 | 2 | 1-Research specific testing frameworks (e.g., Jest for JavaScript, Pytest for Python) based on the team's chosen tech stack. 2-Design the structure of the test suite 5-Refine QA and CI/CD plans based on Week 1 feedback | 0 | 2 | 2 | 0 | 0 | 4 | 0 | 0 | -Use ChatGPT design the test suite structure. Used the ideas to create a proposal for the team -(Use Codeium) Try to write unite testing as a starting point and adapted it for our project's structure | 1.Write test structure document/Diagram - finish SPPP for now 2.prepare for Iteration 0 presentation(slide part) 3.Finish sample unit test code - serve as an example | 1. Dependency on Code: Still waiting for the first meaningful code from the development team to write relevant tests. The sample test is just a placeholder. 2. Environment Differences: My local environment (Node.js/Python version) might be different from the CI environment (GitHub Actions), which could cause problems later | 1. Try to get a preview of the first module they are building, so I can start writing real tests. 2. Document the required software versions in a README.md file. Next step is to configure the GitHub Actions environment to use those specific versions. | 1. Integrate the actual unit test runner into the GitHub Actions pipeline. 2. Write the first real unit tests for an initial code module from a developer. 3. Research and design a strategy for integration/end-to-end (E2E) testing. 4. Team meeting to review progress and adjust priorities. | 10

## Contribution_Xiwen
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/11 - 09/17 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/18 - 09/26 | 15 | 14 | 1 | 0 – Learning: Learn Jira basics, tutorials on issue tracking; explore Vibecoding tool. 1 – Requirement Analysis: Discuss frontend API requirements with team. 2 – Design: Join discussion on frontend page design; review and share template. 3 – Implementation: No major coding this week, only small code review. 4 – Test: Not started this week. 5 – Communication/Management: Team discussions on frontend functions and Jira usage. 6 – Configuration/Environment: Set up Jira environment, explore how to configure project board. 7 – Unclassified: None this week. | 5 | 3 | 2 | 1 | 1 | 1 | 2 | 0 | Used ChatGPT to understand Jira usage and compare with project templates.,used Copilot to generate frontend code examples (needed adjustments). | Collected requirements for frontend API functions.Found and shared a template for frontend design.Joined the discussion on frontend page layout. | Not familiar with Jira, lack of large project experience.Need more communication to clarify task assignments. | Continue Jira learning, aim to create and manage tasks independently.Ask team lead for clearer task allocation and responsibilities. | 0 – Continue Jira tutorial, practice task tracking. 1 – Help refine frontend requirements. 2 – Prepare initial draft of frontend API documentation. | 20

## Contribution_Zihan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: implement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/11 - 09/17 | 7.5 | 6.5 | 1 | 0 – learn git and Jira 1 – define requirements 2 – thinking the construction of the model and the application of data 5 – Team discussions on frontend functions and Jira usage, disscuss with team member ideas and details 6 – Set up environment, explore how to configure project board. | 3 | 0.5 | 0.5 | 0 | 0 | 1.5 | 1 | 0 | Used ChatGPT to understand Jira usage and compare with project templates, find the reason and solve the problems once git meet any error | clearify consumer's need, discuss with team member which model is suitable. set up the git | Not familiar with Jira, lack of large project experience.Need more communication to clarify task assignments. | desigh the ML model ,start tring some small test.Continue Jira learning, aim to create and manage tasks independently. | 0 – Continue Jira tutorial, practice task tracking. 1 – Help refine data analysis requirements. 2 – Prepare initial draft of model | 10
2 | 09/18 - 09/26 | 10.5 | 9.5 | 1 | 0 – learn git and Jira 1-anaylsis the input and requiement, construct the framework 2-design the algorithm and thinging how to implement 7-small group disscussion | 1 | 2 | 5 | 0 | 0 | 0 | 0 | 1.5 | use chatGPT and claude help to brainstrom about the doablity and anaylsis shortage of each algorithm | build a general idea about the ml algorithm clearify the specific piece that related to the ml | ml implementation The accuracy rate of the algorithm | planing to try regression and see the results. Based on those results, make improvements. | 0-learn and compare different alg and model 2-combine suitable alg 3-4- implement and testing model and see the accuracy 5-disscuss with team member about the design and implement | 10